## Project Budget
Project Budget
List every cost by phase. Compare estimates with actuals as invoices come in; variance and contingency update automatically.
Project | [Website redesign] |  |  | Estimated total
Total budget | 48000 |  |  | Contingency reserve
Contingency (%) | 10% |  |  | Estimate + contingency
Spent so far
Budget remaining
Phase | Line item | Vendor | Estimated | Actual | Variance | Status | Notes
Planning | Discovery workshops | Agency | 3500 | 3500 |  | Paid
Planning | User research | Agency | 4000 | 4600 |  | Paid
Design | UX & wireframes | Agency | 6000 | 6000 |  | Paid
Design | Visual design | Agency | 7500 | 7200 |  | Invoiced
Build | Front-end development | Freelancer | 9000 |  |  | Pending
Build | CMS setup | Freelancer | 4500 |  |  | Pending
Build | Hosting & domain (year 1) | Host | 600 | 540 |  | Paid
Content | Copywriting | Writer | 3000 |  |  | Pending
Content | Photography | Photographer | 2500 |  |  | Pending
Launch | QA & testing | Agency | 2000 |  |  | Pending
Launch | Launch ads | Google Ads | 1500 |  |  | Pending
TOTAL